## Cover Page
E-Banking Management System
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Safoora Afzal,Prakash Gupta,Sathwika Kodam,John Emmanuel
| Role | POD Leader,POD Members
| Signature | Safoora Afzal - 2126180 Prakash Gupta-2118838 Sathwika Kodam- 2126145 John Emmanuel-2125035
| Date | 2022-05-30
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog E-Banking Management System
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Registration Page | User | Ability of the system to open registration form it should validate the fundamental details of the users, save the user details in the Database and allow user login. | 1.When the user clicks on the Registration form it should re-direct the Registration form.User needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name,email, Gender, Contact Number, Password. 3. Clicking ‘Submit’ should validate the datatype constraints for each field. 4. User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field level validation, save the information in the database 6. Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. | Critical | Sprint 1 | 5
US_2 | User Authentication | User | Ability of the system to authenticate the credentials of the registered User and assign roles to the user | 1. A registered user – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. 2. A user whose registration is rejected – is unable to login and get the credentials authenticated, the user is presented with relevant error messages: Invalid User ID (or) Incorrect Password | Critical | Sprint 1 | 8
US_3 | Login Page | Admin,User | Ability of the system to access the login form,validate the user details and allow User to login. | 1. When the admin/user clicks on the login in, it should re-direct to login in form 2. User needs to fill some of the basic attributes/fields as mentioned below in requirement: email, Password 3. Clicking ‘Submit’ should validate the datatype constraints for each field 4. Post-successful field level validation, save the information in the database 5. Upon saving the information in the database, display the message, "successfully login". | Critical | Sprint 1 | 13
US_4 | Update Profile | Admin | Ability of the system to allow user to update the profile details dynamically. | 1. When the Admin clicks on the "Update Profile" ,there he should search the Customer with the Account number .Then it should be able to show the last entered details of Customer . 2. User should be able to edit the fields in the form. 3. Clicking ‘Submit’ should validate the datatype constraints for each field 4. User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field level validation, save the information in the database. | Medium | Sprint 1 | 13
US_5 | Add Account | Admin | Ability of the system to allow Admin to create new account the account and save account details to the database. | 1. Admin on clicking the "Add Account" or Open Accout should be able to add new account. 2.First Admin should able to select the Customer then select the account type and enter minimum amount required to open the Accont. 2 Clicking ‘Submit’ should validate the datatype constraints for each field. 3 Failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red. 4 Post-successful field level validation, save the information in the database. | Critical | Sprint 2 | 13
US-6 | View All Accounts | Admin | Ability of the system to allow the admin to view all the accounts . | 1. Admin on clicking the "View All Accounts" should be able to view all the accounts present in the database. | Critical | Sprint 2 | 8
US_7 | View All Customers | Admin | Ability of the system to allow the admin to view all the accounts . | 1. Admin on clicking the "View All Customers" should be able to view all the Customers present in the database. | Critical | Sprint 2 | 8
US-8 | Deposit | Admin | Ability of the system to allow Admin to Deposit money. | 1. Admin on clicking "Deposit Money" will be asked to enter the Account no and need to fill the input fields like transaction date and amount. 2. When admin submit the amount, it will get deposited and available amount is updated. | Critical | Sprint 3 | 13
US-9 | Withdraw | Admin | Ability of the system to allow Admin to withdraw money. | 1. Admin on clicking "Withdraw Money" will be asked to enter the Account no and needs to fill some of the basic attributes/fields as mentioned below in requirement: 2.By Clicking on "Withraw" button it should validate the datatype constraints for each field,and check weather the transfer amount entered is less than available amount then, withdraw money is sucessful and available amount will be updated. 3. If amount entered is more than available amount, transfering will be rejected and Admin will be notified to enter valid amount. | Critical | Sprint 3 | 13
US-10 | Transfer | Admin | Ability of the system to allow Admin to transfer money. | 1. When Admin Clicks on "Transfer Money" will be asked to search for Acount number and need to fill some of the basic attributes.fields as mention in the requirement such as Transaction date,Amount,Receiver's Account holder details. 2. By Clicking on "Transfer" button it should validate the datatype constraints for each field,and check weather the transfer amount entered is less than available amount then, money tranferred is sucessful and available amount will be updated. 3. If amount entered is more than available amount, transfering will be rejected and user will be notified to enter valid amount. | Critical | Sprint 3 | 13
US-11 | Balance Enquiry | Admin | Ability of the system to allow user to check the balance ammount in his account. | 1.When the Admin clicks on the Balance Enquiry ,then it asks admin to enter the Account number to search an then it display the Balance Amount of the Acount holder | Critical | Sprint 3 | 13
US-12 | Bank Charges | Admin | Ability of the system should collect bank charges from the Users. | 1.The Admin should be able to apply the bank fine charges of Rs.100 if the customer balance amount is less than 3000. | Critical | Sprint 3 | 8
US-13 | User Home Page | User | Ability of the System to retrieve the details of the Customer from Database | 1.When User Open his Home page he should be able to access all the functionalities of the user. 2.User Should be able to view all his details retrieved from the database | Critical | Sprint 4 | 13
US-14 | Beneficiary | User | Ability of the System to fetch the beneficiary data and save Beneficiary data in to the database. | 1.When the User Clicks the Bneficiary ,he should be able to view all the Beneficiary details. 2.User Should be able to add the new beneficiary details by filling some of the basic attributes/fields as mentioned below in requirement:Beneficiary Name,Bankname,Account Number and Maximum Limit. 3. Clicking ‘Add Benediciary' should validate the datatype constraints for each field add add beneficiary details to the database. | Critical | Sprint 4 | 13
US-15 | Transfer to Beneficiary | User | Ability of the System to transfer money to the beneficiary | 1.When the user click on "Trensfer to Beneficiary " then he needs to select the beneficiary and need to fill the fields such as Transfer Amount. 2.If amount entered is more than available amount, transfering will be rejected and user will be notified to enter valid amount. | Critical | Sprint 4 | 13
US-16 | Transaction History | User | Ability of the system to allow admin to view all transaction history. | 1. Admin on clicking the "Transaction History" should be able to view all the particular user trasactions present in the database . | Critical | Sprint 4 | 13

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000