## Cover Page
Employee Management System
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Sana Firdaus,Satyam Sharma,Mohd Jeeshan,Prem Kumar R |  | Puran Chandra Rao
| Role | POD Leader,POD Members
| Signature | Sana Firdaus(2134267)Satyam Sharm(2134509) Mohd Jeeshan(2135908)Prem Kumar R(2134700)
| Date | 2022-07-21
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog Employee Management System Project ID: NTADM22JF060/POD-5 C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog E-Banking Management System Project ID: INTADM22JF025/POD-4 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Registration Page | 5
Task_1 | Designing Page |  | Safoora Afzal |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Form Validation |  | Sathwika Kodam |  | 1 | 5 | 4 | 5 | 1 | 2
Task_3 | Register/Login Button Functionality |  | Sathwika Kodam |  | 2 | 0.5 | 5 | 4 | 0 | 2
Task_4 | Saving User Data to Database |  | Prakash Gupta |  | 2 | 0.5 | 5 | 4 | 0 | 2
User Story #2 | User Authentication | 8
Task_1 | Sending User Credentials to backend |  | Safoora Afzal |  | 9 | 4 | 0.5 | 6 | 4 | 0
Task_2 | Handling user login functionality |  | John E. |  | 7 | 0.5 | 8 | 0 | 2 | 4
Task_3 | Assigning Role to User |  | Prakash Gupta |  | 7 | 7 | 9 | 3 | 0 | 1
Task_4 | Connect button to admin login screen |  | Prakash Gupta |  | 1.5 | 8 | 5 | 5 | 0.5 | 2
User Story #3 | Login Page | 13
Task_1 | Designing Page |  | Safoora Afzal |  | 4 | 9 | 4 | 4 | 6 | 0.5
Task_2 | Register/Login Button Functionality |  | Sathwika Kodam |  | 0.5 | 1.5 | 1.5 | 2 | 1.5 | 1
User Story #4 | Update Profile | 13
Task_1 | Designing Page |  | Sathwika Kodam |  | 9 | 4 | 2 | 0.5 | 3 | 0
Task_2 | Dynamic Page Update |  | Safoora Afzal |  | 9 | 6 | 1 | 2 | 0 | 0.5
Task_3 | Writing Controller for the API request |  | John E. |  | 4 | 0 | 2 | 1 | 4 | 2
Task_4 | Function to Update the record |  | Prakash Gupta |  | 4 | 0.5 | 1 | 0 | 0 | 2
TOTAL |  |  |  |  | 67 | 51.5 | 51 | 36.5 | 22

## Sprint -2
Sprint Backlog E-Banking Management System Project ID: INTADM22JF025/POD-4 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #5 | Add Account | 13
Task_1 | Designing Page |  | Safoora Afzal |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Displaying Customer Name in Dropdown |  | Sathwika Kodam |  | 8 | 5 | 3 | 0.5 | 1 | 0
Task_3 | Writing Controller for the API request |  | John E. |  | 4 | 2 | 1 | 0.5 | 0.5 | 1
Task_4 | Save Account to DB |  | Prakash Gupta |  | 4 | 3 | 1 | 0 | 0 | 2
User Story #6 | View All Accounts | 8
Task_1 | Design screen |  | Safoora Afzal |  | 5 | 2 | 1 | 0.5 | 0 | 0
Task_2 | Fetching Data from Database |  | John E. |  | 6 | 3 | 2 | 1 | 0.5 | 0
User Story #7 | View All Customers | 8
Task_1 | Design screen |  | Sathwika Kodam |  | 5 | 2 | 1 | 0.5 | 0 | 0
Task_2 | Fetching Data from Database |  | Prakash Gupta |  | 6 | 3 | 2 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 46 | 23 | 12 | 5 | 4.5 | 4

## Sprint-3
Sprint Backlog E-Banking Management System Project ID: INTADM22JF025/POD-4 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #8 | Deposit | 13
Task_1 | Designing Page |  | Safoora Afzal |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Controller For Deposit Money |  | John E. |  | 8 | 5 | 3 | 0.5 | 1 | 0
Task_3 | Function for deposit money in Backend |  | Prakash Gupta |  | 4 | 2 | 1 | 0.5 | 0.5 | 1
User Story #9 | Withdraw | 13
Task_1 | Designing Page |  | Sathwika Kodam |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Controller For Withdraw Money |  | John E. |  | 8 | 5 | 3 | 0.5 | 1 | 0
Task_3 | Function for withdraw money in Backend |  | Prakash Gupta |  | 4 | 2 | 1 | 0.5 | 0.5 | 1
User Story #10 | Transfer | 13
Task_1 | Designing Page |  | Safoora Afzal |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Controller For Transfer Money |  | John E. |  | 8 | 5 | 3 | 0.5 | 1 | 0
Task_3 | Function for transfer money in Backend |  | Prakash Gupta |  | 4 | 2 | 1 | 0.5 | 0.5 | 1
User Story #11 | Balance Enquiry | 13
Task_1 | Designing Page |  | Sathwika Kodam |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Controller For Balance Enquiry |  | Prakash Gupta |  | 8 | 5 | 3 | 0.5 | 1 | 0
Task_3 | Function for balance enquiry in Backend |  | John E. |  | 4 | 2 | 1 | 0.5 | 0.5 | 1
User Story #12 | Bank Charges | 8
Task_1 | Designing Page |  | Safoora Afzal |  | 5 | 2 | 1 | 0.5 | 0 | 0
Task_2 | Backend Functionality |  | Prakash Gupta |  | 6 | 3 | 2 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 91 | 45 | 23 | 9.5 | 14.5 | 8

## Sprint-4
Sprint Backlog E-Banking Management System Project ID: INTADM22JF025/POD-4 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #13 | User Home Page | 13
Task_1 | Designing Page |  | Sathwika Kodam |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Retrieving Data from Database |  | John E. |  | 8 | 5 | 3 | 0.5 | 1 | 0
User Story #14 | Beneficiary | 13
Task_1 | Designing Page |  | Safoora Afzal |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Fetch Beneficiary Dta |  | John E. |  | 8 | 5 | 3 | 0.5 | 1 | 0
Task_3 | Save Beneficiary Data |  | Prakash Gupta |  | 4 | 2 | 1 | 0.5 | 0.5 | 1
User Story #15 | Transfer to Beneficiary | 13
Task_1 | Designing Page |  | Sathwika Kodam |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Controller For Transfer Money |  | John E. |  | 8 | 5 | 3 | 0.5 | 1 | 0
Task_3 | Function for transfer money in Backend |  | Prakash Gupta |  | 4 | 2 | 1 | 0.5 | 0.5 | 1
User Story #16 | Transaction History | 13
Task_1 | Designing Page |  | Safoora Afzal |  | 8 | 3 | 1 | 1 | 2 | 1
Task_2 | Fetching Data from DB Beneficiary Dta |  | Prakash Gupta |  | 8 | 5 | 3 | 0.5 | 1 | 0
TOTAL |  |  |  |  | 72 | 36 | 18 | 7 | 13 | 6

## Data (hidden)
In-Progress
Completed
N/A